## Sheet1
PROPOSED TIMELINE FOR REGIONS
NB: This timeline is set for a June 30 Financial year end and subsequent AGM. If your Region's time period is different, please adjust the months in Column D
Month | Activity | By whom | Date to be completed
July/August | Regions/Divisions to meet with clubs and confirm BV requirements for 2021-22 implementation | Divisions/clubs | August 15th
Discuss change and implementation date
Queries to be raised with BV, copy to Division and Region Board
BV Region and Boundary Committee to attend Division/Region 2nd (or subsequent) meetings (online or face-to-face)
August | Regions/Divisions to establish a working party with Regions/Divisions nominating potential representatives | Divisions/Region | August 30th
Working parties to meet with current Region Board
Develop strategy for moving forward with implementation
Review Consitution template (NB: Bowls Victoria released a revised version in July 2020)
BV Region and Boundary Committee to respond to Region/Division/Working Party queries (online or face-to-face)
September | Confirm constitution template, raise any queries with BV for clarification (see BV information pack for templates) | Region Secretary | September 30th
| Gather information on playing conditions from Current Divisions for the upcoming season | Working Party
Collate information on how competitions and events (including pennant) for divisions are developed
October | Treasurers of Regions/Divisions to meet to discuss proposed budget for 2021-22 |  | October 30th
Finalise constitution and present for review by Bowls Victoria
Draft Regulations created by the Working Party (see BV information pack for templates)
November | Working Party for Region to decide on committees | Working Party | November 30th
Document the Expression of Interest process for committees (see BV information pack for templates)
December | Finalise Regulations and present for review by Bowls Victoria | Working Party/ | December 30th
| Region to host a Special General Meeting to adopt the new Region Constitution | Region Secretary
Confirm playing areas
January | New Region Constiution to be lodged with CAV (Bowls Victoria to cover the lodgement costs) | Region Secretary | January 30th
Advertise nomination process for Region Board to ensure clarity for Clubs/Members
February |  | Region Secretary | February 28th
March | Open Expression of Interest process for Committee positions | Region Secretary | March 30th
Open nomination process for Board positions
April | Meet with proposed Board Members to discuss portfolios | Region Board | April 30th
| Review nominations for committees/strategy to fill places if required | nominees
May | Conduct Divison AGM's where divisons are dissolved | Divisions | May 30th
Confirm nominations for Region Board 2021-22
June | Region AGM - commence under the new constitution | Region Board | June 30th
Confirm new Board and Committees